## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Afreen | 2002-03-01 | LLM not responding due to API misconfiguration | Sprint 1 | Afreen | Functional | Fixed API key issue | 2003-03-01 | Closed | Resolved after config fix
2 | Afreen | 2005-03-01 | Incorrect prompt output formatting | Sprint 1 | Afreen | UI/Logic | Improved prompt templates | 2006-03-01 | Closed | Formatting corrected
3 | Afreen | 2012-03-01 | Calculator tool returning wrong values | Sprint 2 | Afreen | Functional | Fixed calculation logic | 2013-03-01 | Closed | Tested successfully
4 | Afreen | 2013-03-01 | Weather API mock failing randomly | Sprint 2 | Afreen | API | Added error handling | 2014-03-01 | Closed | Stable now
5 | Afreen | 2015-03-01 | Agent not invoking tools correctly | Sprint 2 | Afreen | Integration | Updated prompt instructions | 2016-03-01 | Closed | Tool usage fixed
6 | Afreen | 2022-03-01 | Agents not sharing context properly | Sprint 3 | Afreen | Functional | Implemented shared memory | 2023-03-01 | Closed | Working fine
7 | Afreen | 2023-03-01 | Memory not persisting across sessions | Sprint 3 | Afreen | Data | Fixed memory config | 2024-03-01 | Closed | Persistence achieved
8 | Afreen | 2025-03-01 | Agent communication delay | Sprint 3 | Afreen | Performance | Optimized chaining logic | 2026-03-01 | Closed | Improved speed
9 | Afreen | 2001-04-01 | API endpoint failing intermittently | Sprint 4 | Afreen | API | Fixed routing issue | 2001-04-01 | Closed | Stable endpoints
10 | Afreen | 2002-04-01 | Frontend not receiving API response | Sprint 4 | Afreen | Integration | Fixed CORS issue | 2002-04-01 | Closed | Frontend-backend synced

## Sheet2
Logical
User Interface
Maintainability
Standards
Others